## Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2020
Municipality of Hinatuan
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Exten-sions, if any | Remarks
[5 empty] | % of Comple-tion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT:
Project Counterpart Fund | Hinatuan, SDS | 2000000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Lot Purchase (Relocation Area) | Hinatuan, SDS | 6500000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Extension of Legislative Building | Hinatuan, SDS | 1500000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Improvement of Municipal Stage | Hinatuan, SDS | 600000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
TOTAL |  | 10600000 |  |  | 0 | 0
ECONOMIC DEVELOPMENT:
Livelihood Support Program | Hinatuan, SDS | 880730.6 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Loan Amortization MDFO | Hinatuan, SDS | 4300000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Construction of Multi-purpose Seaweeds Warehouse at Loyola | Loyola, HSDS | 1000000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Rehabilitation of Roads and Bridges | Hinatuan, SDS | 5000000 | Jan. 2020 | Dec. 2020 | 7.16% | 358007.8 |  | In Progress
Road Concreting | Hinatuan, SDS | 7000000 | Jan. 2020 | Dec. 2020 | 2.413% | 168892.22 |  | In Progress
Rehabilitation of Pocto Foot Bridge | Pocto, HSDS | 1930000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
TOTAL |  | 20110730.6 |  |  | 0.095729 | 526900.02
ENVIRONMENTAL MANAGEMENT:
Completion of Eco-Park Perimeter Fence | Hinatuan, SDS | 400000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Construction of MRF | Hinatuan, SDS | 300000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Construction of Additional Residual Containment Area | Hinatuan, SDS | 300000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Construction of Additional Septic Vault | Hinatuan, SDS | 500000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
Acquisition of Lot for Final Disposal | Hinatuan, SDS | 1000000 | Jan. 2020 | Dec. 2020 | 0% | 0 |  | Not started
TOTAL |  | 2500000 | 0 | 0 | 0 | 0
TOTAL |  | 33210730.6 | 0 | 0 | 0.095729 | 526900.02
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARILOU M. MURIO | [5 empty] | SHEM G. GARAY
Municipal Budget Officer | [5 empty] | Municipal Mayor