## Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2021
Municipality of Hinatuan
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Exten-sions, if any | Remarks
[5 empty] | % of Comple-tion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT:
Project Counterpart Fund | Hinatuan, SDS | 1500000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Lot Purchase (Relocation Area) | Hinatuan, SDS | 5000000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Food Provision | Hinatuan, SDS | 100000 | Jan. 2021 | Dec. 2021 | 98.43% | 98430 |  | On going
Purchase of Vaccines & Testing Kits | Hinatuan, SDS | 1150000 | Apr. 2021 | Dec. 2021 | 30.24% | 347807 |  | On going
Purchase of Hygiene Kits | Hinatuan, SDS | 50000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Miscellaneous Expenses | Hinatuan, SDS | 200000 | Jan. 2021 | Dec. 2021 | 72.8% | 145607.1 |  | On going
TOTAL |  | 8000000 |  |  | 7.398% | 591844.1
ECONOMIC DEVELOPMENT:
Completion of Municipal Gym (Phase III) | Hinatuan, SDS | 5000000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Loan Amortization MDFO | Hinatuan, SDS | 4100000 | Apr. 2021 | Dec. 2021 | 48.88% | 2004099.59 |  | On going
Memorial Park Development (Extension Site) | Hinatuan, SDS | 2000000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Construction of Warehouse | Hinatuan, SDS | 3000000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Purchase & Installation of Slaughter House Equipment | Hinatuan, SDS | 3000000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Slaughter House Water Supply System | Hinatuan, SDS | 1500000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Multi-Specie Hatchery Water Supply Project | Hinatuan, SDS | 1500000 | Apr. 2021 | Dec. 2021 | 0% | 0 |  | Not started
Construction of Drainage System (Poblacion) | Hinatuan, SDS | 1000000 | Jan. 2021 | Dec. 2021 | 97.4% | 974044.35 |  | On going
Dugmanon Drainage System | Hinatuan, SDS | 1000000 | Apr. 2021 | Dec. 2021 | 96.09% | 960862.1 |  | On going
Completion of Pocto Bridge Rehabilitation | Pocto, HSDS | 500000 | Apr. 2021 | Dec. 2021 | 0% |  |  | Not started
Rehabilitation of Roads and Bridges | Hinatuan, SDS | 4000000 | Jan. 2021 | Dec. 2021 | 31.32% | 1252635.9 |  | On going
Construction of Barangay Roads Leading to Emerging Tourist Destination | Hinatuan, SDS | 1409000 | Jan. 2021 | Dec. 2021 | 29.19% | 411225 |  | On going
Extensiom of Legislative Building | Hinatuan, SDS | 1000690.4 | Apr. 2021 | Dec. 2021 | 2.593% | 25950 |  | Not started
TOTAL |  | 29009690.4 |  |  | 19.4% | 5628816.94
ENVIRONMENTAL MANAGEMENT:
TOTAL |  | 0 | 0 | 0 | - | 0
TOTAL |  | 37009690.4 | 0 | 0 | 16.81% | 6220661.04
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD MARILOU M. MURIO | [5 empty] | SGD SHEM G. GARAY
Municipal Budget Officer | [5 empty] | Municipal Mayor
ADD: SUPPLEMENTAL & REALIGNMENT
COVID-19 | 3273290.95
Completion of ER Landmark | 4100000
Tourist Assistance Center Improvement | 50000
Establishment of Water System for Fresh Water Source for Multi-Specie Hatchery | 1500000
TOTAL | 8923290.95
Quarter 1, 2020 | 33210730.6
GRAND TOTAL FOR 2ND QUARTER, 2020 | 42134021.55
42134021.55
0
-5124331.15