## Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2022
Municipality of Hinatuan
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Exten-sions, if any | Remarks
[5 empty] | % of Comple-tion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT:
Livelihood Subsidy to Farmers | Hinatuan, SDS | 1000000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
TOTAL |  | 1000000 |  |  | 0% | 0
ECONOMIC DEVELOPMENT:
Construction of Farmers Information Technology (FITS) | Hinatuan, SDS | 19000000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
Loan Amortization - DBP | Hinatuan, SDS | 9880000 | Jan. 2022 | Dec. 2022 | 4.359% | 430704.92 |  | On going
Purchase of Meat Van | Hinatuan, SDS | 1800000 | Apr. 2022 | Jun. 2022 | 0% | 0 |  | Not yet started
RAPID Project Counterpart Fund | Hinatuan, SDS | 1125000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
Completion of Seaweeds MP Warehouse | Hinatuan, SDS | 1000000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
Construction of Tourism Facilities | Hinatuan, SDS | 4720000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
Restoration of Rehab. Of Small Water Impounding Proj. | Hinatuan, SDS | 1000000 | Jan. 2022 | Dec. 2022 | 0% | 0 |  | Not yet started
Completion of Municipal Slaughter House | Hinatuan, SDS | 1000000 | Jan. 2022 | Dec. 2022 | 89.98% | 899812.61 |  | On going
Rehabilitation of Roads | Hinatuan, SDS | 5000000 | Jan. 2022 | Dec. 2022 | 11.74% | 587155.23 |  | On going
Road Improvement | Hinatuan, SDS | 2875000 | Jan. 2022 | Dec. 2022 | 18.64% | 535940.15 |  | On going
TOTAL |  | 47400000 |  |  | 5.176% | 2453612.91
ENVIRONMENTAL MANAGEMENT:
Dugmanon Drainage System | Dugmanon, HSDS | 1000000 | Jan. 2022 | Dec. 2022 | 59.36% | 593608.37 |  | On going
TOTAL |  | 1000000 |  |  | 59.36% | 593608.37
TOTAL |  | 49400000 | 0 | 0 | 6.168% | 3047221.28
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD MARILOU M. MURIO | [5 empty] | SHEM G. GARAY
Municipal Budget Officer | [5 empty] | Municipal Mayor
ADD: SUPPLEMENTAL & REALIGNMENT
COVID-19 | 3273290.95
Completion of ER Landmark | 4100000
Tourist Assistance Center Improvement | 50000
Establishment of Water System for Fresh Water Source for Multi-Specie Hatchery | 1500000
TOTAL | 8923290.95
Quarter 1, 2020 | 33210730.6
GRAND TOTAL FOR 2ND QUARTER, 2020 | 42134021.55
42134021.55
0
7265978.45